## group info
RPA # 3 Risk Management planning processes
PMC 444 NEE
IT Project Mgmt. Fundamentals, Tools, and Techniques
Mohsen Sabet
Student ID: 113205165
Project: SenecaSync
Professor : Krishna Kishore
Date: 22 November, 2023

## Risk identification matrix
Risk ID | Risk Name | Risk Description | Risk Owner
R01 | Technical Integration Delays | Delays in integrating SenecaSync with Blackboard Ultra due to unforeseen technical challenges. | Tech Lead
R02 | Budget Overrun | Project expenses exceed the allocated budget due to unforeseen costs or underestimation. | Finance Manager
R03 | Insufficient User Adoption | The app is not widely adopted by students due to lack of awareness or interest. | Marketing Lead
R04 | Data Privacy Breaches | Risks associated with handling sensitive student data, leading to potential privacy violations. | Legal & Compliance
R05 | Mobile Platform Compatibility | Issues with ensuring the app works seamlessly across various mobile platforms (iOS, Android). | Development Team
R06 | Inaccurate Requirement Analysis | Incorrect or incomplete analysis of requirements leading to a product that does not meet user needs. | Project Manager
R07 | Stakeholder Engagement Issues | Difficulty in getting consistent engagement or feedback from stakeholders, leading to misaligned expectations. | Project Manager
R08 | Regulatory Compliance Failure | Failure to comply with educational data regulations or standards, leading to legal issues. | Legal & Compliance Team
R09 | Technical Debt Accumulation | Accumulation of technical debt due to rushed development or insufficient testing, leading to long-term issues. | Technical Lead
R10 | Resource Availability | Shortages or delays in acquiring necessary resources, including personnel or technology. | Resource Manager
R11 | Dependency on External Vendors | Critical project components relying on external vendors, which might lead to delays or quality issues. | Procurement Manager
R12 | Network Infrastructure Overload | The college's network infrastructure might not handle the increased traffic, leading to performance issues. | IT Department
R13 | User Interface Design Flaws | The user interface design might not be intuitive or user-friendly, affecting user adoption and satisfaction. | UX/UI Designer
R14 | Inadequate Testing | Incomplete or insufficient testing leading to undetected bugs or issues in the final product. | Lead
R15 | Delay in Project Milestones | Delays in achieving project milestones due to various unforeseen factors, impacting the overall timeline. | Project Manager
R16 | Security Vulnerabilities | Potential security vulnerabilities in the app, leading to risks of data breaches or unauthorized access. | Security Analyst

## Qualitative Risk Analysis
Risk ID | Risk Name | Risk Description | Risk Owner | Probability | Probability Value | Impact | Impact Value | Risk Score | Estimated Cost Impact (CAD)
R01 | Technical Integration Delays | Delays in integrating SenecaSync with Blackboard Ultra due to unforeseen technical challenges. | Tech Lead | Low | 0.74 | High | 0.74 | 0.5476 | 75000
R05 | Mobile Platform Compatibility | Issues with ensuring the app works seamlessly across various mobile platforms (iOS, Android). | Development Team | Low | 0.66 | Medium | 0.66 | 0.4356 | 40000
R15 | Delay in Project Milestones | Delays in achieving project milestones due to various unforeseen factors, impacting the overall timeline. | Project Manager | Low | 0.61 | Medium | 0.62 | 0.3782 | 60000
R06 | Inaccurate Requirement Analysis | Incorrect or incomplete analysis of requirements leading to a product that does not meet user needs. | Project Manager | High | 0.49 | Medium | 0.69 | 0.3381 | 50000
R12 | Network Infrastructure Overload | The college's network infrastructure might not handle the increased traffic, leading to performance issues. | IT Department | High | 0.44 | High | 0.72 | 0.3168 | 18000
R16 | Security Vulnerabilities | Potential security vulnerabilities in the app, leading to risks of data breaches or unauthorized access. | Security Analyst | Medium | 0.33 | High | 0.83 | 0.2739 | 90000
R07 | Stakeholder Engagement Issues | Difficulty in getting consistent engagement or feedback from stakeholders, leading to misaligned expectations. | Project Manager | Medium | 0.33 | Medium | 0.65 | 0.2145 | 25000
R04 | Data Privacy Breaches | Risks associated with handling sensitive student data, leading to potential privacy violations. | Legal & Compliance | Medium | 0.32 | Medium | 0.66 | 0.2112 | 80000
R14 | Inadequate Testing | Incomplete or insufficient testing leading to undetected bugs or issues in the final product. | Lead | Medium | 0.68 | Low | 0.29 | 0.1972 | 45000
R02 | Budget Overrun | Project expenses exceed the allocated budget due to unforeseen costs or underestimation. | Finance Manager | Medium | 0.25 | High | 0.75 | 0.1875 | 100000
R13 | User Interface Design Flaws | The user interface design might not be intuitive or user-friendly, affecting user adoption and satisfaction. | UX/UI Designer | Medium | 0.44 | Medium | 0.33 | 0.1452 | 28000
R03 | Insufficient User Adoption | The app is not widely adopted by students due to lack of awareness or interest. | Marketing Lead | Medium | 0.52 | Low | 0.23 | 0.1196 | 30000
R10 | Resource Availability | Shortages or delays in acquiring necessary resources, including personnel or technology. | Resource Manager | Medium | 0.15 | High | 0.79 | 0.1185 | 20000
R08 | Regulatory Compliance Failure | Failure to comply with educational data regulations or standards, leading to legal issues. | Legal & Compliance Team | Low | 0.25 | Medium | 0.32 | 0.08 | 70000
R11 | Dependency on External Vendors | Critical project components relying on external vendors, which might lead to delays or quality issues. | Procurement Manager | Medium | 0.32 | Low | 0.18 | 0.0576 | 35000
R09 | Technical Debt Accumulation | Accumulation of technical debt due to rushed development or insufficient testing, leading to long-term issues. | Technical Lead | Medium | 0.11 | Medium | 0.37 | 0.0407 | 55000
High Probability: More than 70% chance of occurring.
Medium Probability: Between 30% and 70% chance of occurring.
Low Probability: Less than 30% chance of occurring.
High Impact: Major impact on project scope, budget, or timeline.
Medium Impact: Moderate impact, can be managed with adjustments.
Low Impact: Minor impact, little to no adjustments needed.

## QUALIFIED RISKS
Risk ID | Risk Name | Risk Description | Risk Owner | Probability | Probability Value | Impact | Impact Value | Risk Score | Estimated Cost Impact (CAD)
R01 | Technical Integration Delays | Delays in integrating SenecaSync with Blackboard Ultra due to unforeseen technical challenges. | Tech Lead | Low | 0.74 | High | 0.74 | 0.5476 | 75000
R05 | Mobile Platform Compatibility | Issues with ensuring the app works seamlessly across various mobile platforms (iOS, Android). | Development Team | Low | 0.66 | Medium | 0.66 | 0.4356 | 40000
R15 | Delay in Project Milestones | Delays in achieving project milestones due to various unforeseen factors, impacting the overall timeline. | Project Manager | Low | 0.61 | Medium | 0.62 | 0.3782 | 60000
R12 | Network Infrastructure Overload | The college's network infrastructure might not handle the increased traffic, leading to performance issues. | IT Department | High | 0.44 | High | 0.72 | 0.3168 | 18000
R16 | Security Vulnerabilities | Potential security vulnerabilities in the app, leading to risks of data breaches or unauthorized access. | Security Analyst | High | 0.33 | High | 0.83 | 0.2739 | 90000
R07 | Stakeholder Engagement Issues | Difficulty in getting consistent engagement or feedback from stakeholders, leading to misaligned expectations. | Project Manager | Medium | 0.33 | Medium | 0.65 | 0.2145 | 25000
R04 | Data Privacy Breaches | Risks associated with handling sensitive student data, leading to potential privacy violations. | Legal & Compliance | Medium | 0.32 | Medium | 0.66 | 0.2112 | 80000
R14 | Inadequate Testing | Incomplete or insufficient testing leading to undetected bugs or issues in the final product. | Lead | Medium | 0.68 | Low | 0.29 | 0.1972 | 45000
R02 | Budget Overrun | Project expenses exceed the allocated budget due to unforeseen costs or underestimation. | Finance Manager | Medium | 0.25 | High | 0.75 | 0.1875 | 100000
R06 | Inaccurate Requirement Analysis | Incorrect or incomplete analysis of requirements leading to a product that does not meet user needs. | Project Manager | Medium | 0.49 | Medium | 0.69 | 0.1725 | 50000
R13 | User Interface Design Flaws | The user interface design might not be intuitive or user-friendly, affecting user adoption and satisfaction. | UX/UI Designer | Medium | 0.44 | Medium | 0.33 | 0.1452 | 28000
R03 | Insufficient User Adoption | The app is not widely adopted by students due to lack of awareness or interest. | Marketing Lead | Medium | 0.52 | Low | 0.23 | 0.1196 | 30000
R10 | Resource Availability | Shortages or delays in acquiring necessary resources, including personnel or technology. | Resource Manager | Low | 0.15 | High | 0.79 | 0.1185 | 20000
R08 | Regulatory Compliance Failure | Failure to comply with educational data regulations or standards, leading to legal issues. | Legal & Compliance Team | Medium | 0.25 | Medium | 0.32 | 0.08 | 70000
R11 | Dependency on External Vendors | Critical project components relying on external vendors, which might lead to delays or quality issues. | Procurement Manager | Medium | 0.32 | Low | 0.18 | 0.0576 | 35000
R09 | Technical Debt Accumulation | Accumulation of technical debt due to rushed development or insufficient testing, leading to long-term issues. | Technical Lead | Medium | 0.11 | Medium | 0.37 | 0.0407 | 55000
Quadrant Analysis for Risk Impact and Probability
Upper-Right Quadrant (High Impact, High Probability):
Risks Identified: Risks R01, R05, and R15 are located in this quadrant. These represent the risks that are both highly likely to occur and that would have a substantial impact on the project. They should be given the highest priority for mitigation actions.
Mid-Right Quadrant (Moderate to High Impact, Moderate to High Probability):
Risks Identified: R06, R12, and R16 fall into this space. These risks have a moderate to high chance of occurring and could have a significant negative effect on the project. They should be carefully monitored and managed with well-defined response plans.
Central Area (Moderate Impact, Moderate Probability):
Risks Identified: Risk R02 is nearly central, indicating a balanced moderate impact and likelihood. This risk should be addressed with standard risk management measures.
Lower-Center Quadrant (Low to Moderate Impact, Moderate Probability):
Risks Identified: R03, R13, and R14 are clustered around a moderate likelihood of occurrence with a lower impact. These risks should be managed through routine risk management procedures but don't require as immediate or intense focus as higher-impact risks.
Lower-Left Quadrant (Low Impact, Low Probability):
Risks Identified: Risks R08, R09, and R11 are placed in this quadrant, suggesting they are not very likely to happen and would not have a significant impact if they did. While these risks should not be ignored, they can be addressed with less urgency.

## Quantitative Risk Analysis
We'll rate risks from 0 to 1 (0 is low, 1 is high). Then, we'll find the Risk Factor by multiplying Impact and Probability. Higher Risk Factor means more critical risk.
Risk ID | Risk Name | Risk Description | Risk Owner | Probability | Probability Value | Impact | Impact Value | Risk Score | Estimated Cost Impact (CAD)
R02 | Budget Overrun | Project expenses exceed the allocated budget due to unforeseen costs or underestimation. | Finance Manager | Low | 0.25 | High | 0.75 | 0.1875 | 100000
R16 | Security Vulnerabilities | Potential security vulnerabilities in the app, leading to risks of data breaches or unauthorized access. | Security Analyst | Low | 0.33 | High | 0.83 | 0.2739 | 90000
R04 | Data Privacy Breaches | Risks associated with handling sensitive student data, leading to potential privacy violations. | Legal & Compliance | Low | 0.32 | Medium | 0.66 | 0.2112 | 80000
R01 | Technical Integration Delays | Delays in integrating SenecaSync with Blackboard Ultra due to unforeseen technical challenges. | Tech Lead | High | 0.74 | High | 0.74 | 0.5476 | 75000
R08 | Regulatory Compliance Failure | Failure to comply with educational data regulations or standards, leading to legal issues. | Legal & Compliance Team | Low | 0.25 | Medium | 0.32 | 0.08 | 70000
R15 | Delay in Project Milestones | Delays in achieving project milestones due to various unforeseen factors, impacting the overall timeline. | Project Manager | Medium | 0.61 | Medium | 0.62 | 0.3782 | 60000
R09 | Technical Debt Accumulation | Accumulation of technical debt due to rushed development or insufficient testing, leading to long-term issues. | Technical Lead | Medium | 0.11 | Medium | 0.37 | 0.3168 | 55000
R06 | Inaccurate Requirement Analysis | Incorrect or incomplete analysis of requirements leading to a product that does not meet user needs. | Project Manager | High | 0.49 | Medium | 0.69 | 0.0759 | 50000
R14 | Inadequate Testing | Incomplete or insufficient testing leading to undetected bugs or issues in the final product. | Lead | Low | 0.68 | Low | 0.29 | 0.1972 | 45000
R05 | Mobile Platform Compatibility | Issues with ensuring the app works seamlessly across various mobile platforms (iOS, Android). | Development Team | Medium | 0.66 | Medium | 0.66 | 0.4356 | 40000
R11 | Dependency on External Vendors | Critical project components relying on external vendors, which might lead to delays or quality issues. | Procurement Manager | Low | 0.32 | Low | 0.18 | 0.0576 | 35000
R03 | Insufficient User Adoption | The app is not widely adopted by students due to lack of awareness or interest. | Marketing Lead | Medium | 0.52 | Low | 0.23 | 0.1196 | 30000
R13 | User Interface Design Flaws | The user interface design might not be intuitive or user-friendly, affecting user adoption and satisfaction. | UX/UI Designer | Medium | 0.44 | Medium | 0.33 | 0.1452 | 28000
R07 | Stakeholder Engagement Issues | Difficulty in getting consistent engagement or feedback from stakeholders, leading to misaligned expectations. | Project Manager | Medium | 0.33 | Medium | 0.65 | 0.2145 | 25000
R10 | Resource Availability | Shortages or delays in acquiring necessary resources, including personnel or technology. | Resource Manager | Medium | 0.15 | High | 0.79 | 0.1185 | 20000
R12 | Network Infrastructure Overload | The college's network infrastructure might not handle the increased traffic, leading to performance issues. | IT Department | Medium | 0.44 | High | 0.72 | 0.3168 | 18000

## RISK RESPONSE PLANS
Risk ID | Risk Name | Risk Description | Risk Owner | Risk Response Plan
R01 | Technical Integration Delays | Delays in integrating SenecaSync with Blackboard Ultra due to unforeseen technical challenges. | Tech Lead | Mitigation Strategy: Pre-implementation testing: Conduct thorough integration tests before full implementation. Vendor support: Ensure that the vendor provides technical support for integration challenges. Incremental integration: Break down the integration process into smaller, manageable segments. Contingency Plan: Alternative solutions: Have backup integration methods in place. Schedule buffer: Include additional time in the project schedule to account for potential delays. Monitoring: Regular progress reviews to identify and address integration issues early.
R05 | Mobile Platform Compatibility Issues | Challenges in ensuring that SenecaSync functions consistently across various mobile platforms and devices. | Development Team | Mitigation Strategy: Cross-Platform Development Tools: Utilize tools that support cross-platform compatibility to simplify development. Early Prototyping: Create early prototypes for different platforms to identify potential compatibility issues. Regular Testing on Multiple Devices: Conduct ongoing tests across different operating systems and devices. Contingency Plan: Fallback on Web Version: If compatibility issues cannot be resolved, provide a robust web version of SenecaSync. Adjustment in Scope: Prioritize core functionalities for uniformity across platforms if certain features cause compatibility issues. Monitoring: Device Performance Logs: Keep detailed records of app performance on various devices to quickly spot trends in compatibility issues.
R15 | Delay in Project Milestones | Project timelines slipping due to various unforeseen factors, causing delays in reaching key project milestones. | Project Manager | Mitigation Strategy: Critical Path Analysis: Use critical path method to identify key activities and monitor them closely. Resource Leveling: Adjust resource allocation proactively to avoid overloading team members and causing bottlenecks. Frequent Milestone Reviews: Hold regular meetings to assess progress towards milestones and adjust plans as needed. Contingency Plan: Milestone Buffer: Integrate buffer times into the project schedule for critical milestones. Fast-Tracking or Crashing: When delays occur, apply schedule compression techniques like fast-tracking or crashing to get back on track. Monitoring: Milestone Tracking Software: Utilize project management software to track progress in real-time and alert for deviations from the plan.